## Structure
2015-05-12
See Comment
Field Day Committee Chair
Ron KG7OH
PIO - Janice KI6WCK
Press Releases before & After
Register with ARRL
Safety Officer - NEEDED
Operations -
Tom Shehan W7TGS
Planning -
Erv Pereistein KE7QFI
Logistics -
Sandy Meadowcroft KF4JHC
Finance/Administration
Pat Traber KE7QFG
Purchasing / Approvals
Com Unit
NEDDED
Talk-in
Information
CW Station
Dennis AA7DK
SSB Station
Dennis AA7DK
WSPR Station
Ken KF7DUR
GOTA Station
Schedule
Operations
Documentation
Logs & Computers -
Bonus Stations
Solar??
Food Unit
Phyllis Thompson
Planning
Shopping
Consulting - Joe W7LUX
Review of entire event activities
Consulting - Scott KY7A
Review of entire event activities
Activities
Recruiting
Rules
Exhibits and Displays
MESH Network
Rob WB7QDQ
Accounting Unit
Procurment, Time tracking,, Volunteer Log
Note on G10: http://www.arrl.org/field_days/add
Note on P10: Ronald Gerlak: CARC Field Day Safety Officer June 2015 On Field Day you have many people with different skills doing new tasks or things they have not done for a while. They may have experience in some areas, but not in all facets of the tasks that happen. Many talented people just need a little coordination. To paraphrase James Burke of the British Broadcasting Company "You could get hurt or seriously dead using some of this equipment!" A safety officer needs to be appointed to observe and correct problems. Depending on the size of the group it may be part of one person's duties or a specific individual can be kept busy full time. Last year in the space of three minutes while standing on a step ladder, I had people engaging me in a conversation, tying off coax that was being pulled up the tower, and removing tools that were being used. My error. I did not have a ground person deflecting the "help". Do not be helpful. Ask before assisting in activities. The Safety Officer will oversee the following areas: Tower raising and lowering, with a captain in charge to coordinate the multiple people needed. Proper tower climbing procedures Generator placement – noise, ventilation, weather considerations Gasoline storage and generator refueling Grounding of generator Proper AC cordage – appropriate gauge, good condition, connections protected from the weather. Use of Ground Fault Interrupters Guy wires, stakes, AC cords and coax marked for visibility. Guy wire ends, AC cords and coax coiled up to prevent tripping over. Tools picked up and stowed. Night time site lighting Checks for the safety of visitors to the site. RF hazards Is aware of weather conditions, monitors Skywarn frequency. Works with site Security Officer. Is familiar with the Safety Tips section of the ARRL Field Day package. Identifies who has First Aid and CPR or more advanced medical training. Has direct telephone number to community Public Safety Answering Point. Dialing from a cellular telephone gets you to the State Police who then have to transfer it to the proper agency. Equipment needed: First aid kit Fire extinguisher AC testers Barricade tape Hard Hats Climbing harness To borrow a phrase from New England Telephone "Nothing is so important, that it can not be done safely." Bruce Pigott KC1US <http://cpsg.amateur-radio.net/> Flagging tape SO 2006:154

## Responsibilities
CARC FIELD DAY ASSIGNMENTS 2015
| Highlighted in Green = confirmed |  | Updated | 2015-06-11
Notes |  |  |  |  | Comments
C | Logistics Chief | Sandy | Meadowcroft | KF4JHC
| Communications Officer |  |  |  | 2 Meter Station - Talk-in, Information, Field Day Rules, May set up near GOTA station
Safety Guidelines -
| Food Service | Phyllis | Thompson |  | Mexican, RSVP required, $7.00 - $8.00, Catered,
| Rest Rooms | Scott | Martin | KY7A | Use porta pottys or gas station but not the Silver Saddle Tradding Post
C | Operations Chief | Tom | Shehan | W7TGS
A ,B | SSB HF Station Complete | Dennis | Kimbell | AA7DK | W7TB, NADXA members and others that are willing
A, B | CW HF Station Complete | Dennis | Kimbell | AA7DK | W7TB, NADXA members and others that are willing
A | GOTA (Get On The Air) Station Complete | Erv | Perelstein | KE7QFI | KC7KCN, W7LUX - Joe's K3 Radio,
A | Bonus Station |  |  |  | Solar? Wind?
A | WSPR station | Ken | Held | KF7DUR | 80% sure he will be there ("Weak Signal Propagation Reporter". It is a computer program used for weak-signal radio communication between amateur radio operators.)
A | MESH network | Rob | Schmitt | WB7QDQ | (Amateur radio broadband communications system)
C | Exhibits and Displays Open Saturday 10:00 AM - 5:00 PM
| Solar Observing | Joe | Hobart | W7LUX
| Skywarn/National Weather Service |  |  |  | Info on training and membership,
| High Altitude Balloon exhibit |  |  |  | Kaci Heins will be on vacation but will provide posters
| Public Service Booth |  |  |  | Scheduled Activities, Pictures, Brochures, Maps, Sign Up Sheets
| Disaster Simulation | Mike | Burdiss |  | mburdiss@gmail.com
| NADXA QSL and DX Exibit | Ron | Gerlak | KG7OH
CocoNuts Demo (Coconino High School Robotics Team)
Model RC Plane display (demo?)
| Amateur Licensing and Testing |  |  |  | Manuals available, Pictures, Testing schedule
| Portable Solar Demonstration | Tom | Shehan | KG7TGS
| Portable Solar In-Use | Sandy | Meadowcroft | KF4JHC
| ARES |  |  |  | Balloon Launch info and pictures, Training and membership info (Maybe Kaci Hines)
| CERT & Code Red | Diane | Martin | KF7ZCO | Demo Cert To Go Kit and Coconino County Code Red Allert System
| FEMA / ERMA | Mark | Christian | WB8VWC | Northern AZ Emg Coordinator
| Route 66 On The Air | Ron | Gerlak | KG7OH | Set up display and cover the booth
Girl Scouts
C | Planning Chief | Erv | Perelstein | KE7QFI
| Logging program and computers | Paul | Gagnon | N6MA | Has done it in the past
| Rules | Erv | Perelstein | KE7QFI | Class A2 W7TB plus KC7KCN GOTA
| Points | Bob | Wertz | NF7E | Collect the logs and report our scores
C | Finance/Administration Chief | Pat | Traber | KE7QFG
| Volunteers Sign in/out Log | Pat | Traber | KE7QFG
C | PIO/Publicity | Janice | Enlow | KI6WCK | Twitter, Facebook, newspaper, radio, flyers, CARC web, newsletter, politicians, Mayor, Fire Chief, Police Chief, Sherriff, county Supervisors
| Notification on ARRL web site | Janice | Enlow | KI6WCK
| Visitors Log | Janice | Enlow | KI6WCK
C | Safety Officer
| Field Day Safety Guideline | Bob | Drake | AF7EL
Fire Extinguishers
First Aid Kits
Hard Hats
Gloves
Safety Glasses
Ornge or Yellow Safety Tape
First Aid Team - Identify individuals with CPR and First Aid
Ground Rods
| Ground Strap | Ron | Gerlak | KG7OH
| Circuit Trester | Ron | Gerlak | KG7OH
C | Consulting | Scott | Martin | KY7A
C | Consulting | Joe | Hobart | W7LUX
NOTES:
A | Each station Manager will be responsible for obtaining everything required to set up, operate and take down the station including but not limited to: Shelter, antenna(s), cables, radios, other radio equipment, fire extinguishers, first aid kit, generator(s), fuel, cords and operators unless otherwise noted. They will request materials and help from the Logistics Section as a last resort.
B | The computers and logging software for the CW & SSB stations will be supplied by Planning Section. All other stations will supply their own logs.
C | As the normal course of the event progresses the section Chiefs will acquire as much of the needed materials as possible using their own resourcefulness. The Logistics Section will be responsible for obtaining everything needed to supplement the other sections to make the operation a success.
| Reference Web Site | http://fd.ema.arrl.org/FD_ICS.html
ISSUES to remember
Need Safety Officer
Do we have generators?

## Schedule
EVENTS SCHEDULE |  | Friday | [7 empty] | Saturday | [16 empty] | Sunday
| MST (AZ) | 11:00 | Noon | 1:00 | 2:00 | 3:00 | 4:00 | 5:00 | 6:00 | 7:00 | 8:00 | 9:00 | 10:00 | 11:00 | Noon | 1:00 | 2:00 | 3:00 | 4:00 | 5:00 | 6:00 | 7:00 | 8:00 | 9:00 | 10:00 | 11:00 | Midnight | 1:00 | 2:00 | 3:00 | 4:00 | 5:00 | 6:00 | 7:00 | 8:00 | 9:00 | 10:00 | 11:00 | Noon | 1:00 | 2:00
CW Setup
SSB Setup
GOTA Setup
6 Meter Setup
CW Operate
SSB Operate
GOTA Operate
6 Meter Operate
Public Service Booth Setup
Solar Telescope Setup
ARES Booth Setup
Portable Solar Setup
Public Service Booth Open
ARES Booth Open
Solar Generating Demo Open
Solar Observing
Food Served